## Sheet1
Equipment | Task ID | Task Name | Interval Type | Interval Value | Interval Unit | Trigger Context | Tracking Mode | Hours Source | Calendar Rule | Due Threshold (days) | Document Name | Document File/Link | Manual Page | Procedure Summary | Safety/Notes | Owner | Last Done Date | Last Done Hours | Last Done Furnace Hours | Last_Done_Draw | Required Parts | Group | Planning months | Estimated duration min
Capstan System | CAP-MNT-001 | Before every run: clean pulleys + inspect belt + check surface + confirm belt tension | run | 1 | before every run | Routine Maintenance – Before Every Run | event |  |  |  | Capstan Manual (Capstan V2) | Capstan V2.pdf | 6 | 1) Ensure the capstan assembly and surrounding area are scrupulously clean. 2) Clean the guide pulley and capstan pulley with lint-free tissue soaked in methanol. 3) Inspect the urethane belt for resin debris and embedded fibre; clean or replace if required. 4) Ensure urethane belt tension is correct (minimum tension to prevent slipping). 5) Check capstan surface for scratches/lumps that could damage the fibre. | PPE required. Fibre fragments hazard (wear rubber gloves during thread-up). Trap hazard: keep loose clothing/jewellery away; close capstan guard after thread-up. |  |  |  | 0 |  | IPA wipes / cleaning cloth | Per-Draw/Startup | 0 | 30
Capstan System | CAP-MNT-002 | Every 3 months: check bearings are not worn (sealed for life) | calendar | 3 | months | Routine Maintenance – Every Three Months | calendar |  | months | 7 | Capstan Manual (Capstan V2) | Capstan V2.pdf | 7 | Inspect capstan bearings for wear. Bearings are sealed for life; do not lubricate. | Warning: any attempt to lubricate sealed bearings may cause overheating and failure. |  |  |  | 0 |  | Bearing set | 3-Month | 3 | 15
Capstan System | CAP-MNT-003 | As needed: adjust urethane belt tension (cam plate) | conditional | 1 | when slipping / after belt service | Belt Tension procedure | event |  |  |  | Capstan Manual (Capstan V2) | Capstan V2.pdf | 7 | Adjust belt tension using cam plate: slacken cam plate clamping screws, pivot cam plate to desired tension, then re-tighten both screws. | Ensure machine is stopped and guarded before adjustment. |  |  |  | 0 |  | Urethane belt; Drive belt | On-Condition | 0 | 20